## Planing
Action | Date | Sataus | Resource | Resources
Open AM Multiple role (Mostly Open AM work) |  | No Change |  | Manasha
Preparing excel sheet as per Technical format |  | ??? | Priya
Clean UP resource | 2020-05-15 |  | Debashis | Mustafa
Changes in API - getRoleProfile- API - getUserRoles ( List to Map ) | 2020-05-30 | Completed | Debashis
Changes to Directive | 2020-05-30 | Completed | Debashis
Call getUserRoles for module/page | 2020-05-30 | Completed | Debashis/Manasha | Debashis
Cache user roles | 2020-06-15 | Completed
Admin page resource saving properly with computation path | 2020-05-30 | Completed | Manasha | 50%
utility program to get security data loaded | 2020-05-29 | Completed | Debashis | 50%
Anlysis of existing code | 2020-05-11 | Completed
Clean UP Permission group (all APS) | 2020-05-30 | Completed | Debashis
Clean up unwanted Role | 2020-05-30 | Completed | Debashis
Build Menu Item to Replace | 2020-06-30
Sync open AM and application - Update |  |  | Mustafa
Code changes Module/Page/Section - Setup - Adoption Case | 2020-06-02 | Completed | Manasha
Code changes Module/Page/Section - Setup - Investigation | 2020-05-30 | Completed | Manasha
Code changes Module/Page/Section - Setup - Service Case | 2020-06-05 | Completed
Code changes Module/Page/Section - Setup - Intake | 2020-06-09 | Completed |  | Manasha
Code changes Module/Page/Section - Setup - IVE | 2020-06-11 | Completed
Code changes Module/Page/Section - Setup - Finance | 2020-06-16
Role Configuration
Admin Screen issues | 2020-06-15
User exception build
Visibile and Allow check box not able to select and Deselect Properly | 2020-06-30
only active users should be listed | 2020-06-30
When we are viewing the details of the worker most the details displayed are blank | 2020-06-30
Not able to delete the team from UI | 2020-06-30 |  | 10% buffer will be added
Check the functionality of the Menus under the Admin main menu and remove unwanted Menu option | 2020-06-30
Search resources Add filter Resource Type Resource Name Resource Description | 2020-06-30
PERMISSION GROUP - Search | 2020-06-30 | Completed
Role setup - Search Role and permission group | 2020-06-30 | Completed
Fix screen admin issues - Changes for other application( APS,OLM) | 2020-06-30 | Completed
Resource to Role Direct Mapping
Exclude not like PG in pgresource | 2020-06-03 | Completed
Read Write for loading, Reset the module name when we select other permisssion group | 2020-06-03 | Completed
Role add functionality should be reviewed. | 2020-06-03 | Completed
Key Rules :
1. Group roles based dashboard ?? if unable to map the user , then use no dashboard
2. Exception will be handled using direct mapping resources or permission group
3. If Key is not define all will unrestrited
4. By default all will be accessible
5. No Access Blanket tab link will not display
UNIT Test
If has Module level access then Has access to all element level
If search is disabled then button should be viewable and not clickable
if isvisible id false then button should not be viewable
if isvisible id true and isdiable is false then it is viewed and clieckable
if we have multiple buttons say edit and delete, both the button can have different permissions. One can be clicable other can be disabled.
If the value of the isenabled is null then the button should be enabled.
If the resource does not have the path mentioned, it should be viewable and enabled.

## Tabs Information
Tab Name | Resolver Part | HTML changes | Assigned To | Case Type | Date
summary | DONE | DONE |  | Service Cas & Investigation
person | DONE | DONE |  | Service Cas & Investigation
relationship | DONE | DONE |  | Service Cas & Investigation
checklist | DONE | DONE |  | Service Cas & Investigation
contacts | DONE | DONE |  | Service Cas & Investigation
investigation | DONE | DONE |  | Investigation
maltreatmentallegation | DONE | DONE |  | Investigation
ASSESSMENTS | DONE | DONE | MANASA | Service Cas & Investigation
CHILD REMOVAL | DONE | DONE | MANASA | Service Cas & Investigation
SDM | DONE | DONE | KISHORE | Service Cas & Investigation
ASSIGNEMENTS | DONE | DONE |  | Service Cas & Investigation
DECISION | DONE | DONE | KISHORE | Service Cas & Investigation
DOCUMENTS | DONE | DONE | Srikanth | Service Cas & Investigation
SERVICES | DONE | TO BE DONE | KISHORE | Service Cas & Investigation | 2020-06-01
COURT | DONE | DONE | Srikanth | Service Cas & Investigation | 2020-06-01
PLACEMENT | DONE | DONE | Srikanth | Service Case | 2020-06-01
Permanency Plan | TO BE DONE | TO BE DONE | KISHORE | Service Case
Social History | DONE | DONE | KISHORE | Service Case | 2020-06-01
Case plan | TO BE DONE | TO BE DONE | KISHORE | Service Case | 2020-06-01
Service Agreement | TO BE DONE | TO BE DONE | Srikanth | Service Case | 2020-06-01
Participation | TO BE DONE | TO BE DONE | KISHORE | Service Case
Payments | TO BE DONE | TO BE DONE | Srikanth | Service Case
Narrative | TO BE DONE | TO BE DONE | Debashis | Intake
DECISION | TO BE DONE | TO BE DONE | Debashis | Intake
Intake Documents | TO BE DONE | TO BE DONE | Debashis | Intake
placement adoption | TO BE DONE | TO BE DONE | Srikanth | Service case
placement gap | TO BE DONE | TO BE DONE |  | Service case

## RBAC - Role Sheet
| Roles-DHS |  | Read Only Access |  | Data | [21 empty] | Workflow/Functionality | [19 empty] | added 5/23/19
| Front Line Roles |  | Level of Read Only Access | User Dashboard Page | Client Demographics | DRAI (DJS Role) | Client Assessments | Client Legal Information | Client School, Employment Information | Client Health Information (General) | Client Health Information (HIPAA/Diagnoses) | Client Fiscal, Eligibility, and Benefits Information IV - E | Staff Information | Provider Demographic/ Profile Information | Provider Li-cense/Certi-fication Information | Provider Rates-Contract Information | Fund Source Allocation (Payment Stamping Results) | Provider Payment Information | Provider Record (CHECKLIST, INTERVIEWS ETC) | Provider Record (Qarterly, Mid-Licensure, and Relicensure Reports, ETC) | Provider Legal & Medical Information | Child Placement | APS / CPS Screening | APS / CPS Investigation | Case Information | Service Logs & Adjustments | Create a Client | Supervisor Approvals | Add a program/service | Add Placement | Placement Validation | Transfer a case (to another jurisdiction within MD) | Close a case | Re-open a case | Link Clients (formerly merge) | Generate Documents | Upload Files | Add/Create/RE-OPEN/Close Provider | Provider Waiver | Manual Expunge-ment | Edit IV-E Eligibility | AR Receivable- Balance/ Overpayment Letters/ Write Off/ Receipt/ Pmnt Plan | Child Account / SSA/SSI/etc/ Final Dis/Trust Account (Create/Receipt/Disbursement) | Payment Schedule Calendar (Adj) | Direct ECMS Access to upload IV-E docs | Grant provider portal access | Manage Provider Rates
Child Welfare & Adult Services Roles
1 | 1.a. Case Assistant (Family Support Worker) |  | State | Same as Caseworker Dahsboard | FA ** | XX | FA ** | FA ** | FA ** | FA ** | FA ** | RO | RO | RO | RO | RO | XX | RO | RO | RO | RO | RO | RO | RO | FA** | FA** | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO
2 | 1.b. Intake |  | State | Existing | FA | XX | FA | FA | FA | FA | FA | RO | RO | RO | RO | RO | XX | RO | RO | RO | RO | RO | FA | FA | RO | RO | YES | NO | YES | NO | NO | YES* | NO | YES* | YES* | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO
3 | 1.c. Case Worker |  | State | Existing | FA ** | XX | FA ** | FA ** | FA ** | FA ** | FA ** | RO | RO | RO | RO | RO | XX | RO | FA** | FA** | FA** | FA** | FA** | FA** | FA** | FA** | YES | NO | YES | YES | YES * | YES * | YES * | YES * | YES * | YES | YES | YES * | NO | NO | NO | NO | NO | NO | NO | NO
4 | 1.d. Supervisor |  | State | Existing | FA | XX | FA | FA | FA | FA | FA | RO | RO | RO | RO | RO | RO | RO | FA | FA | FA | FA | FA | FA | FA | FA | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES* | YES* | NO | NO | NO | NO | NO | NO
5 | 1.e. Program Coordinator-Manager-Chief | CJAMS_CW_PGMCOORDINATOR | State | Same as supervisor Dahsboard | FA | XX | FA | FA | FA | FA | FA | RO | RO | RO | RO | RO | RO | RO | FA | FA | FA | FA | FA | FA | FA | FA | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | NO | NO | NO | NO
6 | 2.a. Admin-Audit-Monitor-CQI (Central Office) | CJAMS_CW_ADMAUDIT_MON | State | No Dashboard | RO | XX | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
7 | 2.b. Public-Private Providers (Provider Portal) Foster Families and Facilities |  | State | Note: No Dashboard, will be taken care by OLM | RO ** | XX | FA ** | RO ** | RO ** | RO ** | RO ** | XX | RO ** | RO ** | RO | XX |  | RO ** | XX | XX | [6 empty] | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO
8 | 2. c. Administrator of public providers (TBD) |  | State | Note: No Dashboard, will be taken care by OLM | YES YES: YES** (LDSS) YES (Central); YES YES: YES; YES YES: YES** (LDSS) YES (Central); YES YES: YES** (LDSS) YES (Central); YES NO: TBD (LDSS) YES (Central) | YES (Central)
9 | 2.d.i. Provider Management (Public Resource Homes) - LDSS role to manage providers |  | State | Note: No Dashboard, will be taken care by OLM | FA ** | XX | FA ** | FA ** | FA ** | FA ** | FA ** | XX | RO | FA for Public / RO for Private | RO | RO | XX | RO | FA** | FA** | FA** | FA** | FA** | FA** | FA** | FA** | YES | NO | YES | YES | YES * | YES * | YES * | YES * | YES * | YES | YES | YES * | NO | NO | NO | NO | NO | NO | NO | NO |  | Entire Role should be same access as a worker / Supervisor
10 | 2.d.iii. State Private Provider Rates-Contracting (central office role) | CJAMS_CW_PRVDR_CNTRCTNG | State | Note: No Dashboard, will be taken care by OLM | RO | XX | RO | RO | RO | RO | RO | RO | RO | RO | RO | FA | RO | RO | RO | RO | RO | RO | XX | XX | RO | FA | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | YES (OSS) | NO | NO | NO | NO | XX | NO | XX | XX
11 | 2.f. ICPC-ICAMA (central office role) | CJAMS_CW_ICPC_ICAMA | State | No Dashboard | RO | XX | RO | RO | RO | RO | RO | RO | RO | RO | RO | XX | XX | XX | RO | RO | RO | RO | XX | XX | RO | XX | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO | NO
12 | 2.g. Citizen's Review Board for Children | CJAMS_CW_CRBFC | State | No Dashboard | RO | XX | RO | RO | RO | RO | RO | RO | RO | RO | XX | XX | XX | XX | XX | XX | XX | RO | RO - CPS ONLY / XX for APS | RO - CPS ONLY / XX for APS | RO | RO - SERVICE LOGS ONLY / XX for ADJUSTMENTS | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO | NO
13 | 2.h. Legal Rep-Agency Attorney (central office role) | CJAMS_CW_LEGAL_ATTORNEY | State | No Dashboard | RO | XX | RO | FA ** | RO | RO | RO | RO | RO | RO | RO | RO | XX | RO | RO | RO | RO | RO | RO | RO | RO | RO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | NO | YES | NO | NO | NO | NO | NO | NO
14 | 2.i. Professional Service Staff (statewide access) | CJAMS_CW_PROF_STAFF | State | No Dashboard | RO | XX | FA ** | RO | FA ** | FA ** | FA ** | RO | RO | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES ** | YES ** | NO | NO | NO | NO | NO | NO | NO | NO | NO
15 | 2.j. Appeals Coordinator (central office role) |  | State | Existing | RO | XX | RO | FA ** | RO | RO | RO | RO | RO | RO | RO | RO | XX | RO | XX | XX | XX | RO | RO | FA** | FA** | FA** | NO | NO | NO | NO | NO | NO | YES | YES | NO | YES ** | YES ** | NO | NO | YES | NO | NO | NO | NO | NO | NO
16 | 2.l. Independent Living Coordinator (central office role with full statewide access) | CJAMS_CW_INDPD_COORDINATOR | State | No Dashboard | FA | XX | FA | FA | FA | FA | FA | RO | RO | RO | RO | RO | XX | RO | FA | FA | FA | FA | FA | FA | FA | FA | YES | NO | YES | YES | YES | YES | YES | YES | YES | YES | YES | YES | NO | NO | NO | NO | NO | NO | NO | NO
17 | 2.J. Non DHS - CPS Clearance Staff - (office of Child Care) | CJAMS_CPS_CLRNG_STAFF | State | No Dashboard | RO | XX | XX | XX | XX | XX | XX | XX | RO | XX | XX | XX | XX | XX | XX | XX | XX | XX | RO - CPS INVESTIGATIONS / XX for Alternate Responses / XX for APS | RO - CPS INVESTIGATIONS ONLY / XX for APS | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX
18 | 2.K. Non-DHS - DJS Role (TBD) |  |  | Note: No Dashboard, will be taken care by DJS
DJS Roles
19 | Office Administrator | CJAMS_CW_OFC_ADMINISTRATOR | State | No Dashboard | FA | FA | RO | FA | FA | XX | XX | FA | RO | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | RO | XX | YES | NO | NO | NO | XX | YES | YES | YES | ?? | YES | YES | NO | XX | XX | XX | XX | XX | XX | XX | XX
20 | Intake Worker |  | State | Existing | FA | FA | FA | FA | FA | FA | XX | FA | RO | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FA | XX | YES | NO | NO | NO | XX | YES | YES | YES | ?? | YES | YES | NO | XX | XX | XX | XX | XX | XX | XX | XX
21 | Case Management Specialist | CJAMS_CW_CASE_MGMT_SPECIALIST | State | Same as Caseworker Dahsboard | FA | FA | FA | FA | FA | FA | RO | FA | RO | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FA | XX | YES | NO | YES | NO | XX | YES | YES | YES | ?? | YES | YES | NO | XX | XX | XX | XX | XX | XX | XX | XX
22 | Case Management Supervisor | CJAMS_CW_CASE_MGMT_SUPERVISOR | State | Same as supervisor Dahsboard | FA | FA | FA | FA | FA | FA | RO | FA | FA | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FA | XX | NO | YES | YES | NO | XX | YES | YES | YES | ?? | YES | YES | NO | XX | XX | XX | XX | XX | XX | XX | XX
23 | Executive | CJAMS_CW_EXECUTIVE | State | No Dashboard | RO | RO | RO | RO | RO | RO | RO | RO | RO | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | RO | XX | NO | NO | NO | NO | XX | YES | NO | YES | NO | NO | NO | NO | XX | XX | XX | XX | XX | XX | XX | XX
24 | Medical Specialist | CJAMS_CW_MEDICAL_SPECIALIST | State | No Dashboard | RO | RO | RO | XX | XX | FA | FA | XX | RO | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | RO | XX | NO | NO | NO | NO | XX | YES | NO | YES | ?? | YES | YES | NO | XX | XX | XX | XX | XX | XX | XX | XX
25 | Resource Specialist | CJAMS_CW_RESOURCE_SPECIALIST | State | No Dashboard | RO | RO | RO | XX | XX | RO | RO | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | RO | XX | NO | NO | YES | YES | XX | YES | NO | YES | ?? | YES | YES | NO | XX | XX | XX | XX | XX | XX | XX | XX
26 | License & Monitoring Specialist | CJAMS_CW_LICENSE_MONTRNG_SPECIALIST | State | No Dashboard | FA FA FA FA RO RO RO: RO; FA FA FA FA RO RO RO: RO; RO FA FA FA RO RO RO: RO; FA FA FA FA RO XX XX: RO; FA FA FA FA RO XX XX: RO; XX FA FA FA RO FA RO: RO; XX XX RO RO RO FA RO: XX; FA FA FA FA RO XX XX: RO; RO RO RO FA RO RO XX: XX; RO FA FA FA RO RO RO: RO; YES YES YES NO NO NO NO: NO; NO NO NO YES NO NO NO: NO; NO NO YES YES NO NO YES: NO; NO NO NO NO NO NO YES: NO; YES YES YES YES YES YES YES: YES; YES YES YES YES NO NO NO: NO; YES YES YES YES YES YES YES: YES | ?? | YES | YES | YES
27 | External Agency ** | CJAMS_CW_EXTERNAL_AGENCIES |  | No Dashboard | FA FA FA FA RO RO RO: RO; FA FA FA FA RO RO RO: ??; RO FA FA FA RO RO RO: RO; FA FA FA FA RO XX XX: RO; FA FA FA FA RO XX XX: RO; XX FA FA FA RO FA RO: RO; XX XX RO RO RO FA RO: RO; FA FA FA FA RO XX XX: RO; RO RO RO FA RO RO XX: XX; RO FA FA FA RO RO RO: RO; YES YES YES NO NO NO NO: NO; NO NO NO YES NO NO NO: NO; NO NO YES YES NO NO YES: NO; NO NO NO NO NO NO YES: NO; YES YES YES YES YES YES YES: YES; YES YES YES YES NO NO NO: NO; YES YES YES YES YES YES YES: YES | ?? | NO | NO | NO
28 | IT Administrator | CJAMS_CW_IT_ADMINISTRATOR | State | No Dashboard | FA | FA | FA | FA | FA | FA | FA | FA | FA | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | XX | FA | XX | YES | YES | YES | YES | XX | YES | YES | YES | YES | YES | YES | YES | XX | XX | XX | XX | XX | XX | XX | XX
IV-E Roles
29 | 1.a. IV-E Eligibility Specialist |  | State | Existing | FA ** | XX | RO | FA | RO | RO | RO | FA** | RO | RO | RO | RO | RO | RO | XX | RO | XX | RO | RO | RO | RO | FA | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | No | NO | NO | YES | RO | FA | XX | YES | XX
30 | 1.b. IV-E Eligibility Supervisor |  | State | Existing | FA ** | XX | RO | FA | RO | RO | RO | FA** | FA ** | RO | RO | RO | RO | RO | XX | RO | XX | RO | RO | RO | RO | FA | NO | Yes | NO | NO | NO | Yes | Yes | Yes | Yes | YES | YES | No | NO | NO | YES | RO | FA | XX | YES | XX
31 | 1.c. IV-E Eligibility Analyst | CJAMS_IVE_ANALYST | State | Create a role, dashboard is same supervisor | FA ** | XX | RO | FA | RO | RO | RO | FA** | RO | RO | RO | RO | RO | RO | XX | RO | XX | RO | RO | RO | RO | FA | NO | YES | NO | NO | NO | Yes | Yes | Yes | Yes | YES | YES | No | NO | NO | YES | RO | FA | XX | YES | XX
32 | 1.d. IV-E Eligibility Quality Assurance | CJAMS_IVE_QA | State | Create a role, dashboard is same specialist | FA ** | XX | RO | FA | RO | RO | RO | FA** | RO | RO | RO | RO | RO | RO | XX | RO | XX | RO | RO | RO | RO | FA | NO | YES | NO | NO | RO | NO | Yes | Yes | Yes | YES | YES | No | NO | NO | YES | RO | FA | XX | YES | XX
33 | 1.e. IV-E Eligibility Administrator | CJAMS_IVE_ADMIN | State | No Dashboard | FA ** | XX | RO | FA | RO | RO | RO | FA** | FA ** | RO | RO | RO | RO | RO | XX | RO | XX | RO | RO | RO | RO | FA | NO | Yes | NO | NO | RO | Yes | Yes | Yes | Yes | YES | YES | No | NO | NO | YES | RO | FA | XX | YES | XX
34 | 1.f. IV-E Eligibility Administrative Assistant | CJAMS_IVE_ADMIN_ASSISTANT | State | No Dashboard | FA ** | XX | RO | RO | RO | RO | RO | FA** | FA ** | RO | RO | RO | RO | RO | XX | RO | XX | RO | RO | RO | RO | RO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | No | NO | NO | No | RO | RO | XX | YES | XX
35 | 1.g. IV-E Liaison | CJAMS_IVE_LIAISON | State | No Dashboard | RO | XX | RO | FA | RO | RO | RO | RO | RO | RO | RO | N/A | RO | N/A | XX | N/A | XX | RO | N/A | N/A | RO | RO | NO | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | No | NO | NO | No | RO | RO | XX | YES | XX
OLM Roles
36 | Office Administrator |  | State | Repeated twice, Need clarification | NO | XX | XX | XX | XX | XX | XX | XX | NO | RO | RO | RO | XX | RO | RO | RO | RO | RO | RO | RO | NO | NO | XX | NO | NO | XX | XX | NO | XX | XX | XX | YES | YES | NO | No | XX | XX | NO | XX | XX | XX | NO
37 | Licensing Coordinator | CJAMS_CW_LICENSE_COORDINATOR | State | No Dashboard | RO | XX | XX | XX | XX | XX | XX | XX | NO | FA | FA | RO | XX | RO | FA | FA | FA | RO | RO | RO | RO | RO | XX | NO | YES | XX | XX | NO | XX | XX | XX | YES | YES | YES | YES | XX | XX | RO | XX | XX | XX | NO
38 | Program Manager | CJAMS_CW_LICENSE_COORDINATOR | State | Same as supervisor Dahsboard | RO | XX | XX | XX | XX | XX | XX | XX | FA | FA | FA | RO | XX | RO | FA | FA | FA | RO | RO | RO | RO | RO | XX | YES | YES | XX | XX | YES | XX | XX | XX | YES | YES | YES | YES | XX | XX | RO | XX | XX | XX | YES
39 | Executive |  | State | Same as supervisor Dahsboard | RO | XX | XX | XX | XX | XX | XX | XX | FA | RO | FA | RO | XX | RO | RO | RO | RO | RO | RO | RO | RO | RO | XX | YES | NO | XX | XX | YES | XX | XX | XX | YES | YES | NO | YES | XX | XX | RO | XX | XX | XX | YES
40 | QA Coordinator | CJAMS_CW_QA_COORDINATOR | State | No Dashboard | RO | XX | XX | XX | XX | XX | XX | XX | NO | FA | FA | RO | XX | RO | FA | FA | FA | RO | RO | RO | RO | RO | XX | NO | YES | XX | XX | YES | XX | XX | XX | YES | YES | YES | YES | XX | XX | RO | XX | XX | XX | YES
Finance Roles
41 | 2.e. Payment-Finance-central |  | State | Existing | RO | XX | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | FA - Pmnt Dis Type Central Only | XX | RO | XX | RO | XX | XX | RO | FA-Adjustments / RO Service Logs | XX | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | XX | XX | NO | FA* | RO | RO | XX | XX | YES
42 | 2.e.2 Payment-Finance-LDSS |  | State | Existing | RO | XX | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | XX | RO | FA** local to legal / RO statewide legal other jurisdications / XX medical | RO | XX | XX | RO | FA** | XX | NO | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | XX | XX | NO | FA* - Public Providers Only by Local; RO - All Providers | FA* by Local | RO | XX | XX
43 | 2.f. Payment-Finance-supervisor-central |  | State | Existing | RO | XX | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | FA - Pmnt Dis Type Central Only | XX | RO | XX | RO | XX | XX | RO | FA-Adjustments / RO Service Logs | XX | YES | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | XX | XX | NO | FA | RO | FA (Central Office) | XX | XX | YES
44 | 2.f.2 Payment-Finance - supervisor-LDSS |  | State | Existing | RO | XX | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | XX | RO | FA** local to legal / RO statewide legal other jurisdications / XX medical | RO | XX | XX | RO | FA** | XX | YES | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | XX | XX | NO | FA - Public Providers Only by Local; RO - All Providers | FA* by Local | RO | XX | XX
45 | 2.X. Payment-finance-director-LDSS (TBD) |  | State | Will be same as finance supervisor. | RO | XX | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | RO | XX | RO | FA** local to legal / RO statewide legal other jurisdications / XX medical | RO | XX | XX | RO | FA** | XX | YES | NO | NO | NO | NO | NO | NO | NO | YES | YES | NO | XX | XX | NO | FA - Public Providers Only by Local; RO - All Providers | FA by Local | RO | XX | XX

## Current Role
CJAMS_CWINTAKEWORKER
CJAMS_CWCASEWORKER
CJAMS_CWSUEPRVISOR
CJAMS_CENTRAL_FISCAL_STAFF
CJAMS_CENTRAL_FISCAL_SUPERVISOR
CJAMS_CENTRAL_POLICY_STAFF
CJAMS_APPEALS_COORDINATOR
CJAMS_LDSS_FISCAL_STAFF
CJAMS_LDSS_FISCAL_SUPERVISOR
CJAMS_IVE_SPECIALIST
CJAMS_IVE_SUPERVISOR

## Client Demographic - PG
Resource Name | Resource ID | Resource Type (5% Element) | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group (1.. N)
|  |  |  | Read | Write | No Acess
person | person | 3 |  | R | W | NA
involved | person.person.involved | Screen | person | R | W | NA
search | person.involved.search | Element | involved | R | W | NA
addperson | person.involved.addperson | Element | involved | R | W | NA
delete | person.involved.delete | Element | involved | R | W | NA
edit | person.involved.edit | Element | involved | R | W | NA
placement | person.involved.placement | Element | involved | R | W | NA
removal | person.involved.removal | Element | involved | R | W | NA
program | person.involved.program | Element | involved | R | W | NA

## Client Assessment - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
assessment | assessment | Module |  | R | W | NA
assessments | assessment.assessment.assessments | Screen | assessment | R | W | NA
add | assessment.assessments.add | Element | assessments | R | W | NA
edit | assessment.assessments.edit | Element | assessments | R | W | NA
delete | assessment.assessments.delete | Element | assessments | R | W | NA
print | assessment.assessments.print | Element | assessments | R | W | NA
view | assessment.assessments.view | Element | assessments | R | W | NA

## Role
Role | Permission group name
1.a. Case Assistant (Family Support Worker) | Client demographic Create Client No Access, Client demographic Person card Placement
Read Access Blanket | Read Access Blanket
No Access Blanket | No Access Blanket
| user 1 | Read Access Blanket | Investigation.Person.demographic
| user 2 | Read Access Blanket | Investigation.Person.demographic

## Additional Requirement
S.No | Description
1 | we need to have Adoption Caseworker that has more complete view rights even after break the link. The Caseworker role will need to be adjusted so that the caseworker will not see the bio case after break the link has occurred and the child is adopted. Also, IVE worker will need to be able to see the bio case after break the link
2 | Finance need read only access to CW
3 | Super User(same as it currently is for MD CHESSIE)
4 | Auditors - Access to People coming for Audit
5 | Central and Local administartors
6 | OTHS falls under which group?
7 | staff who are able to enter and update the list of services and service demographics found in the Service Log
8 | Access to update the court details on case to some workers
9 | The Citizens' Review Board needs to mirror the current access that they have in MD CHESSIE which includes the ability to notify the LDSS Administrator and Supervisor and to share their CRBC grinding with the department and to allow the department's response to be documented in the system. This is a CCWIS mandatory requirement
10 | Contractors, on the other hand, cannot be grouped with a single access, for example: Maximus is a contractor who will need the statewide view in areas specific to eligibility for FMIS There are contractors who require access to a specific local department and module to allow for screening by the Sobriety Treatment and Recovery Teams (START) Family Mentor contractor in 13 jurisdictions. Baltimore City and contractors assigned to specifically review Lisa-L cases in Baltimore City only. Their access is restricted and must meet the access criteria set by the Office of the Inspector General. Note: Federal and state audit guidelines require the system assigned start and end dates must mirror the contract/MOU/MOA period
11 | IV_E users should be able to edit some details on CW and should be able to send them for approvak

## Placement - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
placement | placement | Module |  | R | W | NA
scplacements | placement.placement.placementlist | Screen | placement | R | W | NA
add | placement.placementlist.add | Element | placementlist | R | W | NA
view | placement.placementlist.view | Element | placementlist | R | W | NA
edit | placement.placementlist.edit | Element | placementlist | R | W | NA
exit | placement.placementlist.exit | Element | placementlist | R | W | NA
viod | placement.placementlist.viod | Element | placementlist | R | W | NA
placementhistory | placement.placementlist.placementhistory | Element | placementlist | R | W | NA
sendforapproval | placement.placementlist.sendforapproval | Element | placementlist | R | W | NA
approvereject | placement.placementlist.approvereject | Element | placementlist | R | W | NA
paymenthistory | placement.placementlist.paymenthistory | Element | placementlist | R | W | NA

## Permanency Plan - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
permanencyplan | permanencyplan | Module |  | R | W | NA
permanencyplanlist | permanencyplan.permanencyplan.permanencyplanlist | Screen | permanencyplan | R | W | NA
add | permanencyplan.permanencyplanlist.add | Element | permanencyplanlist | R | W | NA
view | permanencyplan.permanencyplanlist.view | Element | permanencyplanlist | R | W | NA
edit | permanencyplan.permanencyplanlist.edit | Element | permanencyplanlist | R | W | NA
history | permanencyplan.permanencyplanlist.history | Element | permanencyplanlist | R | W | NA

## placement adoption - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
adoptionplanning | adoptionplanning | Module |  | R | W | NA
tprrecom | adoptionplanning.adoptionplanning.tprrecom | Screen | adoptionplanning | R | W | NA
legalcustody | adoptionplanning.adoptionplanning.legalcustody | Screen | adoptionplanning | R | W | NA
tpr | adoptionplanning.adoptionplanning.tpr | Screen | adoptionplanning | R | W | NA
planning | adoptionplanning.adoptionplanning.planning | Screen | adoptionplanning | R | W | NA
subsidy | adoptionplanning.adoptionplanning.subsidy | Screen | adoptionplanning | R | W | NA
breakthelink | adoptionplanning.adoptionplanning.breakthelink | Screen | adoptionplanning | R | W | NA
save | adoptionplanning.tprrecom.save | Element | tprrecom | R | W | NA
add | adoptionplanning.legalcustody.add | Element | legalcustody | R | W | NA
edit | adoptionplanning.legalcustody.edit | Element | legalcustody | R | W | NA
view | adoptionplanning.legalcustody.view | Element | legalcustody | R | W | NA
add | adoptionplanning.tpr.add | Element | tpr | R | W | NA
edit | adoptionplanning.tpr.edit | Element | tpr | R | W | NA
view | adoptionplanning.tpr.view | Element | tpr | R | W | NA
delete | adoptionplanning.tpr.delete | Element | tpr | R | W | NA
effortsadd | adoptionplanning.planning.effortsadd | Element | planning | R | W | NA
effortsedit | adoptionplanning.planning.effortsedit | Element | planning | R | W | NA
effortsview | adoptionplanning.planning.effortsview | Element | planning | R | W | NA
effortssave | adoptionplanning.planning.effortssave | Element | planning | R | W | NA
emotionaltiesadd | adoptionplanning.planning.emotionaltiesadd | Element | planning | R | W | NA
emotionaltiesedit | adoptionplanning.planning.emotionaltiesedit | Element | planning | R | W | NA
emotionaltiesview | adoptionplanning.planning.emotionaltiesview | Element | planning | R | W | NA
emotionaltiessave | adoptionplanning.planning.emotionaltiessave | Element | planning | R | W | NA
narrativesave | adoptionplanning.planning.narrativesave | Element | planning | R | W | NA
acasave | adoptionplanning.planning.acasave | Element | planning | R | W | NA
acasendtoivesup | adoptionplanning.planning.acasendtoivesup | Element | planning | R | W | NA
acabypassive | adoptionplanning.planning.acabypassive | Element | planning | R | W | NA
checklistsave | adoptionplanning.planning.checklistsave | Element | planning | R | W | NA
approvereject | adoptionplanning.planning.approvereject | Element | planning | R | W | NA
agreementdownload | adoptionplanning.subsidy.agreementdownload | Element | subsidy | R | W | NA
agreementsave | adoptionplanning.subsidy.agreementsave | Element | subsidy | R | W | NA
agreementapprove | adoptionplanning.subsidy.agreementapprove | Element | subsidy | R | W | NA
ratesendforapproval | adoptionplanning.subsidy.ratesendforapproval | Element | subsidy | R | W | NA
rateadd | adoptionplanning.subsidy.rateadd | Element | subsidy | R | W | NA
rateapprove | adoptionplanning.subsidy.rateapprove | Element | subsidy | R | W | NA
rateedit | adoptionplanning.subsidy.rateedit | Element | subsidy | R | W | NA
rateview | adoptionplanning.subsidy.rateview | Element | subsidy | R | W | NA
download | adoptionplanning.subsidy.download | Element | subsidy | R | W | NA
add | adoptionplanning.breakthelink.add | Element | breakthelink | R | W | NA
view | adoptionplanning.breakthelink.view | Element | breakthelink | R | W | NA
edit | adoptionplanning.breakthelink.edit | Element | breakthelink | R | W | NA
createadoptioncase | adoptionplanning.breakthelink.createadoptioncase | Element | breakthelink | R | W | NA
submitforapproval | adoptionplanning.breakthelink.submitforapproval | Element | breakthelink | R | W | NA
approvereject | adoptionplanning.breakthelink.approvereject | Element | breakthelink | R | W | NA

## placement gap - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
gap | gap | Module |  | R | W | NA
application | gap.gap.application | Screen | gap | R | W | NA
disclosurechecklist | gap.gap.disclosurechecklist | Screen | gap | R | W | NA
agreement | gap.gap.agreement | Screen | gap | R | W | NA
annualreviews | gap.gap.annualreviews | Screen | gap | R | W | NA
suspension | gap.gap.suspension | Screen | gap | R | W | NA
submitforapproval | gap.application.submitforapproval | Element | application | R | W | NA
submit | gap.application.submit | Element | application | R | W | NA
submitforapproval | gap.disclosurechecklist.submitforapproval | Element | disclosurechecklist | R | W | NA
submit | gap.disclosurechecklist.submit | Element | disclosurechecklist | R | W | NA
newagreement | gap.agreement.newagreement | Element | agreement | R | W | NA
edit | gap.agreement.edit | Element | agreement | R | W | NA
view | gap.agreement.view | Element | agreement | R | W | NA
addrate | gap.agreement.addrate | Element | agreement | R | W | NA
editrate | gap.agreement.editrate | Element | agreement | R | W | NA
viewrate | gap.agreement.viewrate | Element | agreement | R | W | NA
submit | gap.agreement.submit | Element | agreement | R | W | NA
submitforapproval | gap.agreement.submitforapproval | Element | agreement | R | W | NA
print | gap.agreement.print | Element | agreement | R | W | NA
completioncriteria | gap.agreement.completioncriteria | Element | agreement | R | W | NA
upload | gap.agreement.upload | Element | agreement | R | W | NA
add | gap.annualreviews.add | Element | annualreviews | R | W | NA
save | gap.annualreviews.save | Element | annualreviews | R | W | NA
submit | gap.annualreviews.submit | Element | annualreviews | R | W | NA
edit | gap.annualreviews.edit | Element | annualreviews | R | W | NA
view | gap.annualreviews.view | Element | annualreviews | R | W | NA
review | gap.annualreviews.review | Element | annualreviews | R | W | NA
submit | gap.suspension.submit | Element | suspension | R | W | NA
submitforapproval | gap.suspension.submitforapproval | Element | suspension | R | W | NA
edit | gap.suspension.edit | Element | suspension | R | W | NA

## Social History - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
socialhistory | socialhistory | Module |  | R | W | NA
socialhistorylist | socialhistory.socialhistory.socialhistorylist | Screen | socialhistory | R | W | NA
save | socialhistory.socialhistorylist.save | Element | socialhistorylist | R | W | NA
history | socialhistory.socialhistorylist.history | Element | socialhistorylist | R | W | NA

## Case plan - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
caseplan | caseplan | Module |  | R | W | NA
caseplans | caseplan.caseplan.caseplans | Screen | caseplan | R | W | NA
saveentereddata | caseplan.caseplans.saveentereddata | Element | caseplans | R | W | NA
createcaseplanversion | caseplan.caseplans.createcaseplanversion | Element | caseplans | R | W | NA
downloadcaseplan | caseplan.caseplans.downloadcaseplan | Element | caseplans | R | W | NA
print | caseplan.caseplans.print | Element | caseplans | R | W | NA
sendforapproval | caseplan.caseplans.sendforapproval | Element | caseplans | R | W | NA
delete | caseplan.caseplans.delete | Element | caseplans | R | W | NA
approvereject | caseplan.caseplans.approvereject | Element | caseplans | R | W | NA

## Service Agreement - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
serviceagreement | serviceagreement | Module |  | R | W | NA
serviceagreements | serviceagreement.serviceagreement.serviceagreements | Screen | serviceagreement | R | W | NA
addagreement | serviceagreement.serviceagreements.addagreement | Element | serviceagreements | R | W | NA
review | serviceagreement.serviceagreements.review | Element | serviceagreements | R | W | NA
view | serviceagreement.serviceagreements.view | Element | serviceagreements | R | W | NA
edit | serviceagreement.serviceagreements.edit | Element | serviceagreements | R | W | NA
download | serviceagreement.serviceagreements.download | Element | serviceagreements | R | W | NA
sendforapproval | serviceagreement.serviceagreements.sendforapproval | Element | serviceagreements | R | W | NA
approvereject | serviceagreement.serviceagreements.approvereject | Element | serviceagreements | R | W | NA

## Participation - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
participation | participation | Module |  | R | W | NA
list | participation.participation.list | Screen | participation | R | W | NA

## Payments - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
payments | payments | Module |  | R | W | NA
list | payments.payments.list | Screen | payments | R | W | NA

## intake narrative - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
narrative | narrative | Module |  | R | W | NA
narrativedetails | narrative.narrative.narrativedetails | Screen | narrative | R | W | NA
quickpersonsearch | narrative.narrativedetails.quickpersonsearch | Element | narrative | R | W | NA
saveasdraft | narrative.narrativedetails.saveasdraft | Element | narrative | R | W | NA

## intake Document - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
intakedocument | intakedocument | Module |  | R | W | NA
upload | intakedocument.intakedocument.upload | Screen | intakedocument | R | W | NA
generate | intakedocument.intakedocument.generate | Screen | intakedocument | R | W | NA
scan | intakedocument.upload.scan | Element | upload | R | W | NA
upload | intakedocument.upload.upload | Element | upload | R | W | NA
email | intakedocument.generate.email | Element | generate | R | W | NA
generate | intakedocument.generate.generate | Element | generate | R | W | NA
viewdownload | intakedocument.generate.viewdownload | Element | generate | R | W | NA
download | intakedocument.upload.download | Element | upload | R | W | NA
edit | intakedocument.upload.edit | Element | upload | R | W | NA
delete | intakedocument.upload.delete | Element | upload | R | W | NA

## intake decision - PG
Resourse Name | Resource ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
intakedecision | intakedecision | Module |  | R | W | NA
disposition | intakedecision.intakedecision.disposition | Screen | intakedecision | R | W | NA
cpsintakereport | intakedecision.disposition.cpsintakereport | Element | disposition | R | W | NA
supervisoroverride | intakedecision.disposition.supervisoroverride | Element | disposition | R | W | NA
submitforapproval | intakedecision.disposition.submitforapproval | Element | disposition | R | W | NA

## Summary - PG
Resourse Name | Resourse ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
summary | summary | Module |  | R | W | NA
reportsummary | summary.summary.reportsummary | Screen | summary | R | W | NA
cpsintakereport | summary.reportsummary.cpsintakereport | Element | reportsummary | R | W | NA

## Checklist-PG
Resourse Name | Resourse ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
checklist | checklist | Module |  | R | W | NA
checklists | checklist.checklist.checklists | Screen | checklist | R | W | NA
save | checklist.checklists.save | Element | checklists | R | W | NA

## Relationship - PG
Resourse Name | Resourse ID | Resource Type | Parent Key | Permission Group |  |  |  | Parent Key
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
relationship | relationship | Module |  | R | W | NA
relationships | relationship.relationship.relationships | Screen | relationship | R | W | NA |  | relationship
edit | relationship.relationships.edit | Element | relationships | R | W | NA |  | relationships
save | relationship.relationships.save | Element | relationships | R | W | NA |  | relationships

## Child Removal - PG
Resourse Name | Resourse ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
childremoval | childremoval | Module |  | R | W | NA
details | childremoval.childremoval.details | Screen | childremoval | R | W | NA
removalstatus | childremoval.details.removalstatus | Element | details | R | W | NA
removalhistory | childremoval.details.removalhistory | Element | details | R | W | NA
saveasdraft | childremoval.details.saveasdraft | Element | details | R | W | NA
submitforapproval | childremoval.details.submitforapproval | Element | details | R | W | NA
update | childremoval.details.update | Element | details | R | W | NA
approval | childremoval.details.approval | Element | details | R | W | NA

## Adoption narrative - PG
Resourse Name | Resourse ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
adoptionnarrative | adoptionnarrative | Module |  | R | W | NA
narrative | adoptionnarrative.adoptionnarrative.narrative | Screen | adoptionnarrative | R | W | NA
save | adoptionnarrative.narrative.save | Element | narrative | R | W | NA

## Court - PG
Resourse Name | Resourse ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
court | court | Module |  | R | W | NA
petitiondetails | court.court.petitiondetails | Screen | court | R | W | NA
save | court.petitiondetails.save | Element | petitiondetails | R | W | NA
edit | court.petitiondetails.edit | Element | petitiondetails | R | W | NA
delete | court.petitiondetails.delete | Element | petitiondetails | R | W | NA
view | court.petitiondetails.view | Element | petitiondetails | R | W | NA
hearingdetails | court.court.hearingdetails | Screen | court | R | W | NA
scheduledhearing | court.hearingdetails.scheduledhearing | Element | hearingdetails | R | W | NA
addhearing | court.hearingdetails.addhearing | Element | hearingdetails | R | W | NA
delete | court.hearingdetails.delete | Element | hearingdetails | R | W | NA
view | court.hearingdetails.view | Element | hearingdetails | R | W | NA
edit | court.hearingdetails.edit | Element | hearingdetails | R | W | NA
courtorder | court.court.courtorder | Screen | court | R | W | NA
view | court.courtorder.view | Element | courtorder | R | W | NA
edit | court.courtorder.edit | Element | courtorder | R | W | NA
legalcustody | court.court.legalcustody | Screen | court | R | W | NA
add | court.legalcustody.add | Element | legalcustody | R | W | NA
addinformation | court.legalcustody.addinformation | Element | legalcustody | R | W | NA
delete | court.legalcustody.delete | Element | legalcustody | R | W | NA
view | court.legalcustody.view | Element | legalcustody | R | W | NA
edit | court.legalcustody.edit | Element | legalcustody | R | W | NA

## Documents - PG
Resourse Name | Resourse ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
documents | documents | Module |  | R | W | NA
case | documents.documents.case | Screen | documents | R | W | NA
person | documents.documents.person | Screen | documents | R | W | NA
uploads | documents.case.uploads | Element | case | R | W | NA
scan | documents.case.scan | Element | case | R | W | NA
camera | documents.case.camera | Element | case | R | W | NA
video | documents.case.video | Element | case | R | W | NA
record | documents.case.record | Element | case | R | W | NA
edit | documents.case.edit | Element | case | R | W | NA
delete | documents.case.delete | Element | case | R | W | NA
edit | documents.person.edit | Element | person | R | W | NA
delete | documents.person.delete | Element | person | R | W | NA

## Services - PG
Resourse Name | Resourse ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
services | services | Module |  | R | W | NA
serviceplan | services.services.serviceplan | Screen | services | R | W | NA
servicelog | services.services.servicelog | Screen | services | R | W | NA
addserviceplan | services.serviceplan.addserviceplan | Element | serviceplan | R | W | NA
editserviceplan | services.serviceplan.editserviceplan | Element | serviceplan | R | W | NA
addvisitationplan | services.serviceplan.addvisitationplan | Element | serviceplan | R | W | NA
editvisitationplan | services.serviceplan.editvisitationplan | Element | serviceplan | R | W | NA
deletevisitationplan | services.serviceplan.deletevisitationplan | Element | serviceplan | R | W | NA
savegoal | services.serviceplan.savegoal | Element | serviceplan | R | W | NA
editgoal | services.serviceplan.editgoal | Element | serviceplan | R | W | NA
deletegoal | services.serviceplan.deletegoal | Element | serviceplan | R | W | NA
saveobjective | services.serviceplan.saveobjective | Element | serviceplan | R | W | NA
editobjective | services.serviceplan.editobjective | Element | serviceplan | R | W | NA
deleteobjective | services.serviceplan.deleteobjective | Element | serviceplan | R | W | NA
savecandidacy | services.serviceplan.savecandidacy | Element | serviceplan | R | W | NA
addnewservice | services.servicelog.addnewservice | Element | servicelog | R | W | NA

## Decision - PG
Resourse Name | Resourse ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
decision | decision | Module |  | R | W | NA
disposition | decision.decision.disposition | Screen | decision | R | W | NA
add | decision.disposition.add | Element | disposition | R | W | NA
save | decision.disposition.save | Element | disposition | R | W | NA
confirmclosure | decision.disposition.confirmclosure | Element | disposition | R | W | NA
submit | decision.disposition.submit | Element | disposition | R | W | NA
cpsintakereport | decision.disposition.cpsintakereport | Element | disposition | R | W | NA

## Contacts - PG
Resourse Name | Resourse ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
contacts | contacts | Module |  | R | W | NA
notes | contacts.contacts.notes | Screen | contacts | R | W | NA
meeting | contacts.contacts.meeting | Screen | contacts | R | W | NA
consultreview | contacts.contacts.consultreview | Screen | contacts | R | W | NA
visitationlog | contacts.contacts.visitationlog | Screen | contacts | R | W | NA
addnew | contacts.notes.addnew | Element | notes | R | W | NA
addnew | contacts.meeting.addnew | Element | meeting | R | W | NA
add | contacts.consultreview.add | Element | consultreview | R | W | NA
add | contacts.visitationlog.add | Element | visitationlog | R | W | NA
edit | contacts.notes.edit | Element | notes | R | W | NA
edit | contacts.meeting.edit | Element | meeting | R | W | NA
edit | contacts.consultreview.edit | Element | consultreview | R | W | NA
edit | contacts.visitationlog.edit | Element | visitationlog | R | W | NA
delete | contacts.consultreview.delete | Element | consultreview | R | W | NA
delete | contacts.visitationlog.delete | Element | visitationlog | R | W | NA
save | contacts.notes.save | Element | notes | R | W | NA
save | contacts.meeting.save | Element | notes | R | W | NA
view | contacts.consultreview.view | Element | consultreview | R | W | NA

## SDM - PG
Resourse Name | Resourse Name | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
sdm | sdm | Module |  | R | W | NA
pathway | sdm.sdm.pathway | Screen | sdm | R | W | NA
maltreatmenttype | sdm.sdm.maltreatmenttype | Screen | sdm | R | W | NA
recommendationovveride | sdm.sdm.recommendationovveride | Screen | sdm | R | W | NA
cpsresponsetype | sdm.sdm.cpsresponsetype | Screen | sdm | R | W | NA
changepath | sdm.pathway.changepath | Element | pathway | R | W | NA

## Maltreatment Allegation - PG
Resourse Name | Resourse ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
maltreatmentallegation | maltreatmentallegation | Module |  | R | W | NA
maltreatmentinformation | maltreatmentallegation.maltreatmentallegation.maltreatmentinformation | Screen | maltreatmentallegation | R | W | NA
save | maltreatmentallegation.maltreatmentinformation.save | Element | maltreatmentinformation | R | W | NA
recordmaltreatment | maltreatmentallegation.maltreatmentinformation.recordmaltreatment | Element | maltreatmentinformation | R | W | NA

## Investigation Findings - PG
Resourse Name | Resourse ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
investigationfinding | investigationfinding | Module |  | R | W | NA
investigationfindings | investigationfinding.investigationfinding.investigationfindings | Screen | investigationfinding | R | W | NA
save | investigationfinding.investigationfindings.save | Element | investigationfindings | R | W | NA
completeinvestigation | investigationfinding.investigationfindings.completeinvestigation | Element | investigationfindings | R | W | NA
summaryreport | investigationfinding.investigationfindings.summaryreport | Element | investigationfindings | R | W | NA
expungement | investigationfinding.investigationfindings.expungement | Element | investigationfindings | R | W | NA

## Assignments - PG
e | Resourse ID | Resource Type | Parent Key | Permission Group
|  |  |  | RO Group | WR Group | NA Group | Exception Group
|  |  |  | Read | Write | No Acess
assignment | assignment | Module |  | R | W | NA
cwassignments | assignment.assignment.cwassignments | Screen | assignment | R | W | NA
edit | assignment.cwassignments.edit | Element | cwassignments | R | W | NA
add | assignment.cwassignments.add | Element | cwassignments | R | W | NA